## Sheet1
Phase | Task | Week
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | 1. Project plan | [13 empty] | *Project ends on Monday of week 14
| Complete and submit a Project Plan | Week 1: ALL
2. Set up Raspberry Pi as Server and confirmed communication
| Set up Raspberry Pi as a server | Week 1: Fergus
| Confirm communication between client computer and server (HTTP/SSH) | Week 1: Fergus
3. STM32 Programming via HAL
| Explain common CAN messaging protocol (see document) | Week 1: Nigel
| Implement the CAN messaging protocol by properly setting the filters (code demo) on STM32 | Week 2: Nigel
| Implement Wiring on STM32, push buttons/LED indicators (possible COVID restrictions) | Week 2: ALL
| Able to read CAN messages placed on the CAN bus (Raspberry Pi) and detect up/down request, floor request, door open/close, location of elevator car | Week 2: Ryan
| Develop and implement a test plan to confirm functionality of software/hardware | Week 1: ALL
3. Controls / indicators (virtual and buttons)
| Controls (up/down) built in HTML (possibly add CSS if students work ahead) | Week 1: Fergus/Ryan
| Elevator Car Controls (up/down/floor number) built in HTML (possibly CSS if students work ahead) | Week 1: Fergus/Ryan
4. Finite State Machine (recommended)
| Develop Finite State Machine Logic for Elevator Operation | Week 1: Ryan
2 | 1. User Interface / Client Program
| Fully working and completed front end Graphical User Interface /Webpage to control elevator | Week 2: Fergus
| User action buttons/icons implemented | Week 2: Fergus
| Indicators/lights etc. implemented | Week 3: Fergus/Nigel
| User action buttons developed to make changes to UI that are reflected in the database | Week 2: Fergus/Ryan
| User indicator buttons change - changes in database are reflected in UI | Week 6: Fergus/Ryan
2. Database Repository
| Database set up and accepting values/commands from website | Week 6: Fergus/Ryan
| Database has fields for logging information placed on the CAN bus | Week 6: Nigel
3. Diagnostic Reports
| Produced based on content in database | Week 3: Nigel/Ryan
| Displayed on webpage | Week 3: Nigel/Fergus
4. Server Program
| Users are authorized/authenticated based on username/password | Week 5: Fergus
| Server program provides logging data/accepts commands only from authorized users | Week 6: Fergus
5. Announce floor numbers (Function of the Client or Server Program) for users with Visual Impairments
| Implement a Server Program for announcing the floor numbers | Week 7: Ryan/Nigel
| Speaker on elevator used to announce the current/next floor (speaker already connected to system) | Week 7: Ryan/Nigel
6. Sabbath mode (Function of the Client Program)
| Users may operate the elevator without having to push buttons (e.g. verbally, based on schedule/time) | Week 7: Ryan/Fergus
3 | 1. CAN/LAN network communication
| Research and Implement a CAN/LAN communication bridge | Week 11: Nigel/Ryan
| Ensure activity in CAN network changes values in database | Week 11: Nigel/Ryan
| Changes in User Interface/Website changes value in database and generate CAN messages | Week 11: Fergus/Ryan
| CAN Messages result in changes to database and GUI/Indicators | Week 11: ALL
| Commands from CAN/LAN networks are sent to the controller and move the elevator / indicate floor number | Week 11: ALL
2. Controller Software Written
| CAN Supervisor (Raspberry Pi) relays messages between CAN/LAN Network (see sample program on Rpi) | Week 11: Nigel/Ryan
3. Finite State Machine logic written
| Develop and Implement a finite state machine (using C/C+, PHP, Python to implement logic) | Week 3: Ryan
| 4. Additional capability that shows ingenuity | Week 9: ALL
| 5. Ideas for Capstone (at least 3 per student) | Week 3: ALL
| 6. Final Presentation & Demonstration | Week 10: ALL